## How to Use
Corrective Action Tracker
A free tool from Calgary Safety Consultants to go with our guide, How to Manage Corrective Actions.
How to use this tracker
1. Log it | Enter every corrective action on the Tracker tab the day it's raised, whatever its source: inspections, incidents, hazard reports, hazard assessments, committee recommendations, audits, OHS orders and work refusals.
2. Control it now | Record any immediate action or interim control. An interim control keeps people safe while the permanent fix is arranged; give it an end date.
3. Find the cause | Ask why the hazard exists until you reach something the organization can change. Avoid causes that end with a worker's name.
4. Choose a strong action | Pick the strongest practical control: elimination, substitution or engineering controls before administrative controls and PPE. Write exactly what will change, where and to what standard.
5. Assign it | Give each action one named owner, a priority and a due date. The suggested due date is calculated from the priority; set the real due date in the Due date column.
6. Track and escalate | Review open actions at a regular meeting. Filter the Overdue? column for Yes. Record extensions, with the reason and who approved them, in Notes and extensions.
7. Verify and close | Mark an action Verified and closed only after someone has checked it was done, it works and it didn't create a new hazard. Record who verified it and how, and set an effectiveness check date for priority A and B actions.
Priority key (edit the timeframes on the Lists tab)
A - Critical | Control the hazard immediately, before work continues, and complete the permanent fix as quickly as possible.
B - Serious | Complete as soon as possible, typically within 7 days.
C - Minor | Complete within 30 days or at the next scheduled maintenance.
Columns that calculate automatically (grey)
Suggested due date | Date raised plus the days to complete for the priority on the Lists tab.
Days open | Days from the date raised to the date completed, or to today if the action isn't complete.
Overdue? | Yes if the due date has passed and no completion date is entered. Closed late if it was completed after the due date.
Tips
Keep one list | If inspection forms, incident reports or meeting minutes have their own action sections, copy every action here so nothing is tracked in two places.
Name a person | Assign actions to a person, not a department. Other people can help; one person owns the date.
Use the Summary tab | Review open and overdue actions by priority, the percentage closed on time and the average days to close at your management or committee meetings.
Need more rows? | The Tracker is set up for 250 actions. To add more, copy the last row down; the formulas and drop-downs will copy with it.
General information, not legal advice. Occupational health and safety requirements differ between provinces, territories and federally regulated workplaces, so confirm the requirements that apply to your workplace. Calgary Safety Consultants ¦ calgarysafetyconsultants.ca ¦ 1-888-231-0358

## Tracker
Corrective Action Tracker
Log every corrective action in one place, whatever its source. Fill in the white cells; grey cells calculate automatically.
Company | [6 empty] | Maintained by |  |  |  |  | Legend: | White = enter | Grey = formula | Row 7 is an example. Overwrite it or delete its contents.
Site | [6 empty] | Last reviewed
Ref # | Date raised | Source | Area or location | Hazard or finding | Immediate action or interim control | Cause | Corrective action | Control type | Priority | Owner | Suggested due date | Due date | Status | Date completed | Verified by | Date verified | How it was verified | Effectiveness check due | Days open | Overdue? | Notes and extensions
CA-001 | 2026-10-05 | Inspection | Fabrication bay 2, pedestal grinder G-4 | Tool rest gap about 10 mm and no tongue guard; risk of hand or glove being drawn in. | Grinder tagged out of service; workers directed to grinder G-2. | No pre-use check for grinders; guard parts not stocked. | Install tongue guard, set tool rest to 3 mm or less, add grinders to the pre-use checklist and stock spare guard parts. | Engineering control | A - Critical | Maintenance lead | 2026-10-06 | 2026-10-06 | Verified and closed | 2026-10-06 | Shop supervisor | 2026-10-07 | Observed in place and measured; photo filed with inspection report. | 2026-11-06 | 1 | No | Example row. Replace with your own entries.
Formulas:
Suggested due date = IF(OR([Date raised]="",[Priority]=""),"",[Date raised]+IFERROR(INDEX(Lists!$D5:D7,MATCH([Priority],Lists!$C5:C7,0)),0))
Days open = IF([Date raised]="","",IF([Grey = formula]<>"",[Grey = formula]-[Date raised],TODAY()-[Date raised]))
Overdue? = IF(OR([Date raised]="",[Legend:]=""),"",IF([Grey = formula]<>"",IF([Grey = formula]>[Legend:],"Closed late","No"),IF(TODAY()>[Legend:],"Yes","No")))

## Summary
Corrective Action Summary
Calculated from the Tracker tab. Use these numbers for your monthly or quarterly management review.
As of | 2026-10-07
Priority | Total logged | Open (not closed) | Overdue now | Closed | Closed on time | Closed late | % closed on time | Average days to close
A - Critical | 1 | 0 | 0 | 1 | 1 | 0 | 100% | 1
B - Serious | 0 | 0 | 0 | 0 | 0 | 0 | - | -
C - Minor | 0 | 0 | 0 | 0 | 0 | 0 | - | -
All priorities | 1 | 0 | 0 | 1 | 1 | 0 | 100% | 1
Closed on time and closed late count actions with a completion date. Open counts every logged action not yet marked Verified and closed.
By source | Total | Open
Inspection | 1 | 0
Incident or near miss | 0 | 0
Hazard report or worker concern | 0 | 0
Hazard assessment or JHA | 0 | 0
Committee or representative recommendation | 0 | 0
Audit | 0 | 0
OHS order or compliance notice | 0 | 0
Work refusal | 0 | 0
Other | 0 | 0
By control type | Total | Open
Elimination | 0 | 0
Substitution | 0 | 0
Engineering control | 1 | 0
Administrative control | 0 | 0
PPE | 0 | 0
Combination | 0 | 0
Review questions
• Are any priority A actions overdue? If so, what is needed to close them this week?
• Which actions are stalled waiting on money, parts, people or a decision, and who can unblock them?
• Are the same findings coming back after actions were closed? If so, revisit the cause.
• Are most actions administrative controls or PPE? Look for stronger controls higher in the hierarchy.
• Has everyone who raised a hazard been told what was done?

## Lists
Drop-down lists and priority timeframes
You can edit these lists. Keep the priority codes (A, B and C) at the start of each priority name, because the Summary tab counts on them.
Source | Control type | Priority | Days to complete | Priority meaning | Status
Inspection | Elimination | A - Critical | 1 | Control the hazard immediately, before work continues, and complete the permanent fix as quickly as possible. | Open
Incident or near miss | Substitution | B - Serious | 7 | Complete as soon as possible, typically within 7 days. | In progress
Hazard report or worker concern | Engineering control | C - Minor | 30 | Complete within 30 days or at the next scheduled maintenance. | Extended
Hazard assessment or JHA | Administrative control |  |  |  | Completed - awaiting verification
Committee or representative recommendation | PPE | Days to complete is used for the suggested due date on the Tracker tab. Change the blue numbers to match your own program. Priority A uses 1 day as a placeholder for the permanent fix; the hazard itself must be controlled immediately. |  |  | Verified and closed
Audit | Combination
OHS order or compliance notice
Work refusal
Other